## Sheet1
Task ID | Task Name | Location | Discipline | Planned Start | Planned Finish
OIL-001 | Site Survey & Clearance | Block Baghjan | Civil | 2026-09-01 | 2026-09-05
OIL-002 | Rig Mobilization & Assembly | Well Pad 5 | Logistics | 2026-09-06 | 2026-09-11
OIL-003 | Drilling Surface Hole | Well Pad 5 | Drilling | 2026-09-12 | 2026-09-15
OIL-004 | Casing & Cementing | Well Pad 5 | Drilling | 2026-09-16 | 2026-09-17
OIL-005 | Pipeline Trenching | Sector 4 (Pipeline) | Civil | 2026-09-18 | 2026-09-21
OIL-006 | Pipe Laying and Welding | Sector 4 (Pipeline) | Mechanical | 2026-09-22 | 2026-09-30
OIL-007 | NDT & X-Ray Inspection | Sector 4 (Pipeline) | QA/QC | 2026-10-01 | 2026-10-03
OIL-008 | Hydrotesting | Sector 4 (Pipeline) | QA/QC | 2026-10-04 | 2026-10-07
OIL-009 | Backfilling and Restoration | Sector 4 (Pipeline) | Civil | 2026-10-08 | 2026-10-11
OIL-010 | Well Commissioning | Facility B | Operations | 2026-10-12 | 2026-10-15